## Risk Register
Blue Ridge Family Health Clinic — Information Security Risk Register
Methodology: NIST SP 800-30 Rev.1 qualitative risk assessment (5x5 Likelihood x Impact matrix) ¦ Prepared: July 2026 ¦ Classification: Internal Use Only
ID | Risk Description | Category | Threat Source | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score (L x I) | Risk Level | Existing Controls | Recommended Treatment | Risk Owner | Target Date | Status
R-01 | Phishing email leads to compromised staff O365 credentials | Technical | External attacker | Limited phishing/security awareness training for clinical staff | 4 | 4 | 16 | Critical | Basic email spam filtering; no phishing simulation program | Deploy phishing-resistant MFA on O365; run quarterly simulated phishing campaigns | IT Manager | 2026-09-30 | Open
R-02 | Ransomware encrypts EHR-connected endpoints via compromised workstation | Technical | External attacker / malware | Endpoints lack EDR; inconsistent patch cadence | 3 | 5 | 15 | Critical | Antivirus (signature-based) on workstations; nightly EHR vendor backups | Deploy EDR to all endpoints; enforce automated patch management; test backup restoration quarterly | IT Manager | 2026-10-15 | Open
R-03 | Remote billing staff laptop lost or stolen while unencrypted | Physical/Technical | Theft/loss | Full-disk encryption not enforced on remote laptops | 2 | 4 | 8 | Medium | Laptops issued with standard OS install; no MDM enrollment | Enforce BitLocker/FileVault via MDM; enable remote wipe capability | IT Manager | 2026-09-15 | Open
R-04 | Third-party billing vendor suffers a data breach exposing PHI | Third-Party | Vendor/supply chain | No annual vendor security review; BAA lacks breach-notification SLA | 2 | 5 | 10 | High | Signed Business Associate Agreement (BAA) on file | Require SOC 2 report annually; add 72-hour breach notification clause; add to vendor risk register | Compliance Officer | 2026-11-01 | Open
R-05 | Clinical staff use weak or shared passwords across systems | Administrative | Insider (unintentional) | No enforced password complexity or uniqueness policy | 4 | 3 | 12 | High | Basic 8-character minimum password rule | Enforce password policy via Active Directory GPO; roll out password manager for staff | IT Manager | 2026-08-31 | Open
R-06 | EHR remote access is not protected by multi-factor authentication | Technical | External attacker | Legacy EHR remote portal supports password-only login | 3 | 5 | 15 | Critical | VPN required for remote access; static password login | Enable MFA on VPN and EHR portal immediately; treat as priority remediation | IT Manager | 2026-08-15 | In Progress
R-07 | Outdated/unpatched networked medical devices (BP monitors, scales) | Technical | External attacker / malware | Devices run unsupported firmware; vendor patches applied ad hoc | 3 | 3 | 9 | Medium | Devices isolated on separate VLAN from EHR systems | Establish device inventory and firmware patch schedule with biomedical vendor | Clinical Ops Manager | 2026-12-01 | Open
R-08 | Insufficient security awareness training across all staff roles | Administrative | Insider (unintentional) | Training limited to one-time HIPAA orientation at hire | 4 | 3 | 12 | High | HIPAA training at onboarding only | Implement annual mandatory security awareness training with tracked completion | Compliance Officer | 2026-09-30 | Open
R-09 | No formal, tested incident response plan for security events | Administrative | N/A (process gap) | IR responsibilities undocumented; no defined escalation path | 3 | 4 | 12 | High | Informal verbal escalation to IT Manager | Draft IR plan aligned to NIST SP 800-61; run tabletop exercise within 90 days | Compliance Officer | 2026-10-31 | Open
R-10 | Improper disposal of paper records containing PHI | Physical | Insider (unintentional) | No shredding policy consistently enforced at front-desk stations | 2 | 3 | 6 | Medium | Locked shred bins present in back office only | Add shred bins to all front-desk stations; add disposal step to clean-desk policy | Office Manager | 2026-09-01 | Open
R-11 | Insider unauthorized access to patient records outside job duties | Administrative | Insider (intentional) | EHR access not role-restricted; no access review cadence | 2 | 4 | 8 | Medium | EHR maintains access logs, not actively reviewed | Implement role-based access control; conduct quarterly access reviews and log audits | Compliance Officer | 2026-11-15 | Open
R-12 | Guest Wi-Fi network is not segmented from clinical/EHR network | Technical | External attacker | Flat network architecture; single SSID for guests and staff | 3 | 4 | 12 | High | Guest Wi-Fi password-protected but same VLAN as clinical systems | Segment guest Wi-Fi onto isolated VLAN with no route to clinical network | IT Manager | 2026-08-31 | Open
R-13 | Backup failures or untested disaster recovery leave data unrecoverable | Administrative | N/A (process gap) | Backups run automatically but restoration has never been tested | 2 | 5 | 10 | High | Cloud EHR vendor performs nightly backups per contract | Document DR/BCP plan; perform full restoration test annually; define RTO/RPO | IT Manager | 2026-12-15 | Open
Risk Level Thresholds (Score = Likelihood x Impact):
Low | 1-4
Medium | 5-9
High | 10-14
Critical | 15-25

## 5x5 Heat Map
Likelihood x Impact Heat Map — Risk Count by Cell
Likelihood \ Impact | Impact 1 | Impact 2 | Impact 3 | Impact 4 | Impact 5
Likelihood 5 | 0 | 0 | 0 | 0 | 0
Likelihood 4 | 0 | 0 | 2 | 1 | 0
Likelihood 3 | 0 | 0 | 1 | 2 | 2
Likelihood 2 | 0 | 0 | 1 | 2 | 2
Likelihood 1 | 0 | 0 | 0 | 0 | 0
Cell values = count of risks in the register at that Likelihood/Impact combination (auto-updates via COUNTIFS).